## Sheet1
email notif isac
[14 empty] | username |  | isac
PT. ACSET Indonusa Tbk. | [13 empty] | Password |  | Acset2022
Timeline EDOC [ IMPROVEMENT FROM LEGAL ]
No | Description | Days | Periode |  | % Progress | Status | Mei |  |  |  | Juni |  |  |  | Juli |  |  |  | Agustus |  |  |  | September |  |  |  | Oktober
|  |  | Start | End |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Phase Gathering Requirement
1 | Meeting awal Pembahasan | 1 Hari | 17.02.2023 | 17.02.2023 | 100% | Done | bar: Mei W1
2 | Guidance Penggunaan | 1 Hari | 17.02.2023 | 17.02.2023 | 100% | Done | bar: Mei W1
3 | Membuat Flow Proses | 2 Hari | 01.03.2023 | 03.03.2023 | 100% | Done | bar: Mei W1
4 | Membuat Timeline | 1 Hari | 01.03.2023 | 01.03.2023 | 100% | Done | bar: Mei W1
5 | Membuat Mockup | 7 Hari | 02.05.2023 | 12.05.2023 | 100% | Done | bar: Mei W2
6 | Membuat BRD | 10 Hari | 02.05.2023 | 12.05.2023 | 100% | Done | bar: Mei W2
7 | Review BRD + Revisi | 3 Hari | 15.05.2023 | 17.05.2023 | 100% | Done | bar: Mei W2
Programing Infrastructure
Master Data
1 | Master Location | 5 Hari | 22.05.2023 | 26.05.2023 | 0% | Not Yet | bar: Mei W3
2 | Master Data User - Improvement | 3 Hari | 29.05.2023 | 31.05.2023 | 0% | Not Yet | bar: Mei W4
3 | Master Data Rack | 5 Hari | 01.06.2023 | 07.06.2023 | 0% | Not Yet | bar: Juni W1
Transaksi
1 | Improvement - upload dokumen | 10 Hari | 08.06.2023 | 21.06.2023 | 0% | Not Yet | bar: Juni W1 to Juni W3
- Ditambahkan informasi lokasi fisik | bar: Juni W1 to Juni W3
2 | Permintaan Dokumen Softcopy | 10 Hari | 22.06.2023 | 05.07.2023 | 0% | Not Yet | bar: Juni W3 to Juli W1
2.1. Request Dokumen Soft Copy | bar: Juni W3 to Juli W1
2.2. Approval Atasan Requestor | bar: Juni W3 to Juli W1
2.3. Terima Permintaan | bar: Juni W3 to Juli W1
2.4. Kirim Permintaan Dokumen | bar: Juni W3 to Juli W1
2.5. Approval Atasan Pengirim | bar: Juni W3 to Juli W1
3 | Permintaan Dokumen Hardcopy | 14 Hari | 06.07.20223 | 25.07.2023 | 0% | Not Yet | bar: Juli W1 to Juli W3
3.1. Request Dokumen Hard Copy | bar: Juli W1 to Juli W3
3.2. Approval Atasan Requestor | bar: Juli W1 to Juli W3
3.3. Terima Permintaan | bar: Juli W1 to Juli W3
3.4. Kirim Permintaan Dokumen | bar: Juli W1 to Juli W3
3.5. Approval Atasan Pengirim | bar: Juli W1 to Juli W3
4 | 4.1. Kirim Dokumen ke gudang center | 10 Hari | 26.07.2023 | 08.08.2023 | 0% | Not Yet | bar: Juli W2 to Agustus W1
4.1.1. Kirim dokumen | bar: Juli W2 to Agustus W1
4.1.2. Approval Kirim dokumen | bar: Juli W2 to Agustus W1
4.2. Terima Dokumen digudang center | bar: Juli W2 to Agustus W1
4.2.1. Terima dokumen | bar: Juli W2 to Agustus W1
4.2.1. Approval terima dokumen | bar: Juli W2 to Agustus W1
4.3.1 History Tracking | bar: Juli W2 to Agustus W1
Preparation Golive
1 | SIT | 2 Hari | 07.06.2023 | 11.08.2023 |  | Not Yet | bar: Juni W1 to Agustus W1
2 | User Manual | 5 Hari | 14.08.2023 | 18.08.2023 |  | Not Yet | bar: Agustus W2 to Agustus W3
3 | UAT | 2 Hari | 21.08.2023 | 22.08.2023 |  | Not Yet | bar: Agustus W3
4 | Bugs Fixing | 7 Hari | 23.08.2023 | 29.08.2023 |  | Not Yet | bar: Agustus W3 to Agustus W4
5 | Persiapan Server | 1 Hari | 07.06.2023 | 07.06.2023 |  | Not Yet | bar: Juni W1
5 | Materi Training | 2 Hari | 01.08.2022 | 02.08.2022
6 | Training User | 1 Hari | 03.08.2022 | 03.08.2022
6 | Go Live | 1 Hari | 04.09.2023 | 04.09.2023 |  | Not Yet | bar: September W1
7 | Go Live Support | 30 Hari | 04.09.2023 | 04.10.2023 |  | Not Yet | bar: September W1 to September W4

## Progress
No | Description | Status | Bobot | Not yet | Inprogress | Done | Keterangan
1 | Phase Prepare | Done | 20% |  |  | 20%
2 | Phase Development
| - Improvement Master Data | Not Yet | 5%
| - Improvement Upload data | Not Yet | 5%
| - Dokumen Soft Copy | Not Yet | 15%
| - Request Dokumen Soft Copy | Not Yet
| - Approved Dokumen Soft Copy | Not Yet
| - Kirim Dokumen Soft Copy | Not Yet
| - Terima Dokumen Soft Copy | Not Yet
| - Approved Dokumen Soft Copy | Not Yet
| - Dokumen Hard Copy | Not Yet | 15%
| - Request Dokumen Hard Copy | Not Yet
| - Approved Dokumen Hard Copy | Not Yet
| - Kirim Dokumen Hard Copy | Not Yet
| - Terima Dokumen Hard Copy | Not Yet
| - Approved Dokumen Hard Copy | Not Yet
| - Kirim Dokumen Hard Copy Gudang Center | Not Yet | 15%
| - Kirim Dokumen Hard Copy | Not Yet
| - Approved Dokumen Hard Copy | Not Yet
| - Terima Dokumen Hard Copy | Not Yet
| - Approved Dokumen Hard Copy | Not Yet
| - Report | Not Yet | 5%
3 | Phase Deployment | Not Yet | 10%
4 | Phase Complete | Not Yet | 10%
|  | Total | 100% | 0% | 0% | 20%
|  |  | Total Progress |  | 20%
112
28

## Sheet2 (hidden)
Include >>
Atasan
Request Dokumen Softcopy
Kirim Dokumen Gudang Center
Request Dokumen Hardcopy
Master Data User Managem
Master Data Location
Include >>

## Sheet3 (hidden)
No | NRP | Nama Karyawan | Alamat email | No Telp | Lokasi Project | Jabatan | Group Member | Status
1 | 81170291 | Andri LAW | Andri.law@acset.co | 0813928192 | Cleon Park | Surveyor | Surveyor | Active
2
3
Report Tracking
No | Nama Project | Module | Nama Surveyor | Tgl Pelaksanaan | Easting [Latitude] | Northing [Longitude] | Posisi | Zona
3175012907131001
1 | Cleon Park Apt | UTM | Totok W | 2022-12-07 | 702457.914225178 | 9318091.7503 | Titik 1 | Utara
2 | Cleon Park Apt | UTM | Totok W | 2022-12-07 | 702457.914225178 | 9318091.7503 | Titik 1 | Utara
3 | Cleon Park Apt | Geodetik | Totok W | 2022-12-07 | -6.1660572 | 106.8296 | Titik 1 | Utara
Report Tools Management
No | Nama Project | Module | Nama Surveyor | Tgl Pelaksanaan | Nama Alat | Merk / Brand | No Seri Alat | Tanggal Kirim | Tanggal Terima | Vendor / Tempat pengambilan | Kondisi / kelengkapan | Catatan
1 | Cleon Park Apt | Kalibrasi | Totok W | 2022-12-07 | Theodolite | Yamaha | Q-01-20201 | 13-07-2022 | 13-07-2022 | - | - | -
2 | Cleon Park Apt | Beli Baru | Totok W | 2022-12-07 | Theodolite | Yamaha | Q-01-20201 | 13-07-2023 | 13-07-2023 | ASCC PLUS | Lengkap | -
3 | Cleon Park Apt | Pinjam/sewa | Totok W | 2022-12-07 | Theodolite | Yamaha | Q-01-20201 | 13-07-2024 | 13-07-2024 | ASCC PLUS | Layak Pakai | Ok
4 | Cleon Park Apt | Hilang | Totok W | 2022-12-08 | Theodolite | Yamaha | Q-01-20201 | 13-07-2025 | 13-07-2025 | - | Hilang | -
Report Daily Job
No | Nama Project | Module | Nama Surveyor | Jabatan | Tgl Pelaksanaan | Object Pekerjaan | Nama Customer | Posisi/Jabatan Customer | Tanggal request | Deskripsi singkat pekerjaan | Deskripsi singkat masalah/temuan | Status
1 | Cleon Park Apt | Daily Job Report | Totok W | Staff | 2022-12-07 | Tagging Lokasi | Yamaha | Q-01-20201 | 13-07-2022 | 13-07-2022 | - | Close
2 | Cleon Park Apt | Daily Job Report | Totok W | Staff | 2022-12-07 | Tagging Lokasi | Yamaha | Q-01-20201 | 13-07-2023 | 13-07-2023 | ASCC PLUS | Close
3 | Cleon Park Apt | Daily Job Request | Totok W | Staff | 2022-12-07 | Tagging Lokasi | Yamaha | Q-01-20201 | 13-07-2024 | 13-07-2024 | ASCC PLUS | Open
4 | Cleon Park Apt | Daily Job Request | Totok W | Staff | 2022-12-08 | Tagging Lokasi | Yamaha | Q-01-20201 | 13-07-2025 | 13-07-2025 | - | Close
Report Standard References
No | Tgl Proses | No Dokumen | Nama Dokumen | Tanggal Expired | Status Dokumen
1 | 13-07-2022 | A01-001-2022 | Kepatuhan | 13-10-2022 | Publish
2 | 13-07-2022 | A01-001-2022 | Cara Taging | 13-10-2022 | Publish
3 | 13-07-2022 | A01-001-2022 | Spesifik Alat | 13-10-2022 | Publish
Report Project Case
No | Tanggal Proses | Ditujukan kepada | Subyek | Description
1 | 13-07-2022 | All Member | Memorandum | Mohon dapat dilanjutkan
2 | 13-07-2022 | Surveyor | Surat Teguran | Mohon dapat dilanjutkan
3 | 13-07-2022 | Head | Instruksi kerja | Mohon dapat dilanjutkan